Cumberland Municipal Airport Committee
Minutes –June 17, 2026

Members Present:  Matt Rybarczyk, Otieno Oduor, Jim Anderson and Josh Johnson
City:   
Staff Present :  Rick Brekke
Guest;  None

Agenda/Notes-  
1)  Call to order-  Rick Brekke called the meeting to order at 6.06 PM in the Airport Terminal  Conference room and noted attendance.

2) Public Comments – There was no public in attendance.
3) Secretary Report- Minutes from March 23, 2026 and April 15, 2026 reviewed. Jim Anderson moved motion to approve and Matt Rybarczyk seconded.  Motion carried
4) Treasurer’s Report- and status of budget- currently we are about $5000 in the hole.  Motion to approve treasurer’s report moved by Oduor and seconded by Anderson.  Motion carries.
5) Committee officers-  Committee needs to name a chairperson, treasurer and secretary.  Since not all members were present, discussion was tabled for future discussion.
6) Fuel Pump upgrade- Dispenser has shipped from manufacturer.  Fuel Master has not shipped the computer.  Once we have equipment, it takes about 2 to 3 weeks to install.  Pumps will have cellular and no wi-fi needed.   
7) Hangar Project-  Update given from Karl Kemper of Becher Hoppe indicates that our application for funding most likely met the deadline.  The process should proceed as follows:
Sept 2026- FAA awards design grant to BOA.
Nov 2026-  BOA process grant and execute BH engineering contract.
Nov 2026- Feb 2027- BH design hangar project.
Feb 2027-Mar 2027- Contractor bidding process.
May 2027- BOA submit construction grant application to FAA.
Sep 2027-FAA awards construction grant to BOA.
Nov 2027- BOA process grant and execute construction contracts.
2028- construction begins
8) WIFI- Discussion and comparison between Starlink and Brightspeed.  Starlink commercial package is about $1200/month.  Residential/personal is about $100.  Tabled for decision at a later date.
MasterPlan-  Left out of agenda unintentionally- BOA expected to start process in Nov 2026.  Aeronautical survey will happen not later than September 2026.  
9) General updates for future agenda items – None
10)Adjourn-  Meeting was adjourned at 7.30 PM.  Anderson moved motion         
and Johnson seconded.  Motion carries
